## Sprint 1
Sprint 1 Backlog
| Item # | Description | Est | Actual | By
Very High
|  | Assign Members: Joshua Hoffman: Product Owner Aaron: Scrum Master Sam: Team Member Carey Tyler: Team Member | 0.5 |  | Team
|  | Setup GitHub | 1 |  | Aaron
|  | Link to GitHub in Eclipse | 1 |  | Josh
|  | Link to GitHub in Eclipse | 1 |  | Tyler
|  | Link to GitHub in Eclipse | 1 | 0.25 | Sam
|  | Link to GitHub in Eclipse | 1 |  | Aaron
|  | Add Prof. to GitHub | 0.1 |  | Aaron
|  | Create Product Backlog | 0.5 |  | Josh
|  | Research how to interface UI to Google API webService | 2 |  | Aaron
|  | Research how to output summary data to Google Charts | 2 |  | Sam
|  | Build user interface-window.java (Windows Builder) | 1 |  | Aaron
|  | Human centered design and layout of UI | 1 |  | Aaron
|  | Research how to interface UI to BeetleDev.com webService to calculate BMI | 2 |  | Josh
|  | Look into how to code and output user input for BMI to BeetleDev.com webService to calculate BMI | 2 |  | Josh
|  | Decide which classes and functions to utilize from BeetleDev.com for BMI | 1 |  | Josh
|  | Look at and understand how to utilize code from BeetleDev.com (Also in a jar file on Blackboard | 1 |  | Tyler
|  | Research on UML diagrams | 1 |  | Tyler
|  | Determine what UML diagrams to use | 1 |  | Tyler
|  | Design UML diagrams in MS Viso | 1 |  | Tyler
|  | Modifications to diagrams in MS Viso | 1 |  | Tyler
|  | Code to solicit info from user | 2 |  | Sam
|  | Code to print summary report to console | 2 |  | Aaron/Sam
|  | Code to use Google API with summary data | 4 |  | Aaron/Sam
|  | Integrate Google API web service | 4 |  | Sam
|  | Code to interface to BeetleDev.com for BMI calculations | 4 |  | Josh
|  | Integrate BeetleDev web service | 4 |  | Josh
|  | Junit test for BMI | 2 |  | Tyler
|  | Junit test for Google API | 2 |  | Aaron
|  | Junit test for UI | 2 |  | Sam
|  | Check Style | 2 |  | Sam
|  | Ad-Hoc (Misc) testing summary data output | 4 |  | Aaron
|  | Ad-Hoc (Misc) testing for BMI calculations | 4 |  | Josh
|  | Ad-Hoc (Misc) testing for UI and client output data | 4 |  | Tyler
|  | Ad-Hoc (Misc) testing for Google API chart output | 4 |  | Sam
|  | Error corrections/bug fixes- summary data output | 2 |  | Aaron
|  | Error corrections/bug fixes- for BMI calculations | 2 |  | Josh
|  | Error corrections/bug fixes- for UI and client output data | 2 |  | Tyler
|  | Error corrections/bug fixes- for Google API chart output | 2 |  | Sam
…..
|  | Total | 74.1 | 0.25

## Burndown Chart
Date | Remaining | hrs
2016-10-26 | 14
2016-10-26 | 13.5 | 0.5 | 1 | Assign Members: Mark: Product Owner Aaron: Scrub Master Sam: Team Member
2016-10-26 | 12.5 | 1 | 2 | Setup GitHub
2016-10-26 | 11.5 | 1 | 3 | Link to GitHub / Add Backlogs
2016-10-27 | 10.5 | 1 | 4 | Link to GitHub / (Strike this comment to confirm)
2016-10-27 | 9.5 | 1 | 5 | Add Prof. to GitHub
2016-10-27 | 7.5 | 2 | 6 | View Sample website (Review Calculator)
2016-10-28 | 6.5 | 1 | 7 | Do part 1 of assignment-8(research)
2016-10-30 | 5.5 | 1 | 8 | Create testcase for Calculation to compute Time
2016-10-30 | 3.5 | 2 | 9 | Create testcase for Calculation to compute distance
2016-10-30 | #REF! | #REF! | 10 | Create testcase for Calculation to compute pace
2016-10-31 | #REF! | 1 | 11 | Build user interface-window.java (Windows Builder)
2016-11-01 | #REF! | 1 | 12 | build Class Distance.java
2016-11-01 | #REF! | 1 | 13 | build Class Pace.java
2016-11-01 | #REF! | 2 | 14 | build Class Time.java