## Sprint 1
Sprint 1 Backlog
Description | Assigned Team Member |  | Time (hrs)
|  | Original | Day 1 Spent | Day 1 Left | Day 2 Spent | Day 2 Left | Day 3 Spent | Day 4 Left | Day 5 Left | Day 6 Left | Day 7 Left | Day 7 Left | Day 8 Left | Day 8 Left | Day 9 Left | Day 10 Left
Assign Members: Joshua Hoffman: Product Owner Aaron: Scrum Master Sam: Team Member Carey Tyler: Team Member | Team | 0.5 | 0.5
Setup GitHub | Aaron | 1
Link to GitHub in Eclipse | Josh | 1
Link to GitHub in Eclipse | Tyler | 1
Link to GitHub in Eclipse | Sam | 1 | 0.25
Link to GitHub in Eclipse | Aaron | 1
Add Prof. to GitHub | Aaron | 0.1
Create Product Backlog | Josh | 0.5
Research how to interface UI to Google API webService | Aaron | 2
Research how to output summary data to Google Charts | Sam | 2
Build user interface-window.java (Windows Builder) | Aaron | 1
Human centered design and layout of UI | Aaron | 1
Research how to interface UI to BeetleDev.com webService to calculate BMI | Josh | 2
Look into how to code and output user input for BMI to BeetleDev.com webService to calculate BMI | Josh | 2
Decide which classes and functions to utilize from BeetleDev.com for BMI | Josh | 1
Look at and understand how to utilize code from BeetleDev.com (Also in a jar file on Blackboard | Tyler | 1
Research on UML diagrams | Tyler | 1
Determine what UML diagrams to use | Tyler | 1
Design UML diagrams in MS Viso | Tyler | 1
Modifications to diagrams in MS Viso | Tyler | 1
Code to solicit info from user | Sam | 2
Code to print summary report to console | Aaron/Sam | 2
Code to use Google API with summary data | Aaron/Sam | 4
Integrate Google API web service | Sam | 4
Code to interface to BeetleDev.com for BMI calculations | Josh | 4
Integrate BeetleDev web service | Josh | 4
Junit test for BMI | Tyler | 2
Junit test for Google API | Aaron | 2
Junit test for UI | Sam | 2
Check Style | Sam | 2
Ad-Hoc (Misc) testing summary data output | Aaron | 4
Ad-Hoc (Misc) testing for BMI calculations | Josh | 4
Ad-Hoc (Misc) testing for UI and client output data | Tyler | 4
Ad-Hoc (Misc) testing for Google API chart output | Sam | 4
Error corrections/bug fixes- summary data output | Aaron | 2
Error corrections/bug fixes- for BMI calculations | Josh | 2
Error corrections/bug fixes- for UI and client output data | Tyler | 2
Error corrections/bug fixes- for Google API chart output | Sam | 2
…..
Total |  | 74.1 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining |  | 73.35

## Burndown Chart
Date | Remaining | hrs
2016-10-26 | 14
2016-10-26 | 13.5 | 0.5 | 1 | Assign Members: Mark: Product Owner Aaron: Scrub Master Sam: Team Member
2016-10-26 | 12.5 | 1 | 2 | Setup GitHub
2016-10-26 | 11.5 | 1 | 3 | Link to GitHub / Add Backlogs
2016-10-27 | 10.5 | 1 | 4 | Link to GitHub / (Strike this comment to confirm)
2016-10-27 | 9.5 | 1 | 5 | Add Prof. to GitHub
2016-10-27 | 7.5 | 2 | 6 | View Sample website (Review Calculator)
2016-10-28 | 6.5 | 1 | 7 | Do part 1 of assignment-8(research)
2016-10-30 | 5.5 | 1 | 8 | Create testcase for Calculation to compute Time
2016-10-30 | 3.5 | 2 | 9 | Create testcase for Calculation to compute distance
2016-10-30 | #REF! | #REF! | 10 | Create testcase for Calculation to compute pace
2016-10-31 | #REF! | 1 | 11 | Build user interface-window.java (Windows Builder)
2016-11-01 | #REF! | 1 | 12 | build Class Distance.java
2016-11-01 | #REF! | 1 | 13 | build Class Pace.java
2016-11-01 | #REF! | 2 | 14 | build Class Time.java